## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
3lqYUCWDNUyq7k5-FlpIDmUAM1RC | Hire help | TO DO, this week | Not started | Urgent | Brian Baker;Isabela Almeida | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 0/9 | GOOGLE analytics;IG / FB admin;WEBDEV (wix);IG post creation / management;Katie Todd?;Eileen;Boran;Kate cygan?;Katie Koenig |  | eileen - webdev katie koenig? analytics
4Qiilc6cLU2Z1j77Dx8RVGUACN0u | wix FAQ topics | URGENT - DO THIS NOW | Not started | Important | Brian Baker;Isabela Almeida | Brian Baker | 04/20/2025 |  |  | false | false |  |  | 0/2 | how to check VA letters.. https://news.va.gov/116268/view-download-va-decision-letters-online/; va letters explained https://cck-law.com/veterans-law/types-of-va-decision-letters-explained | WIX SHIT
KimHU3NajUODg-gZXcR4B2UALBDT | L4v ad campaign calendar | TO DO, this week | Not started | Urgent | Brian Baker;Isabela Almeida | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/2 | Fed/Mil holidays: instagram, facebook, email, sms??;Bday outreach: email, sms??
Mw6q29JirE-QC1BG3IWsoWUAPbWG | GAds / Wix conversion tracker | URGENT - DO THIS NOW | Not started | Urgent | Brian Baker;Isabela Almeida | Brian Baker | 04/15/2025 |  |  | false | false |  |  | 0/5 | conversion tracker on form? pages? lander? ;install intaker?;https://support.google.com/google-ads/answer/12215519?sjid=2230791702719779702-NC#zippy=%2Cin-google;SCHEDULE MEETING;requires google tag manager
UZu936IaTkeGn8Ddu1gZDmUAFNjt | Connect Meta Verified Support | URGENT - DO THIS NOW | Completed | Medium | Brian Baker | Isabela Almeida | 04/08/2025 |  |  | false | false | 04/14/2025 | Brian Baker |  |  |  | Brian cannot access Meta Business Suite using his personal login (bakerb4379) 🐊: fixed it?!??? enabled all accounts cross-login, then (personal) meta verified. not sure what did it
-FEccZXBmUKDVdm7MfaZvWUALMgw | ADMIN for g.ads | GOOGLE ANALYTICS | Not started | Medium |  | Brian Baker | 04/22/2025 |  |  | false | false |  |  | 0/1 | cannot link to ads acoount without admin rights
-rt_iSavdk-b8xIuFJpWimUAKHSV | audit SEO of old websites | L4V x Wayback Archive | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/5 | anchor links;copy content, as pertaining to SEO ;URL slugs;SEO tags? ;previous homepage was stuffed with SEO and anchor links
0QvnfPoUAkaxu-feOt1O6GUAI7vJ | Joe's Meta 2fa (debbie mail) | URGENT - DO THIS NOW | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 2/3 | email debbie;receive > enter code via joe's personal fb account;RECEIVED: BBDIGITAL INBOX FOR CODE
0Rb5xvrsUUWpRWJ4nhIXzWUAB-dy | wix mobile - zooming issue | URGENT - DO THIS NOW | Completed | Important |  | Brian Baker | 03/31/2025 |  |  | false | false | 04/28/2025 | Brian Baker | 0/9 | edit mobile site for 3XXpx wide (look this up)... audit with browser inspection>mobile, not wix prvw;background asset does not move, so.... "prebake" the ~translucent blue onto the background image??;change fonts to 13pt+? - https://forum.wixstudio.com/t/having-a-page-zoom-out-on-mobile/41668/3;reconfigure hamburger menu (remove?) ;https://support.wix.com/en/article/accessibility-about-zoomed-content;decrease font sizes - https://support.wix.com/en/article/mobile-live-site-loads-zoomed-inout-on-andr;buttons link to external URL instead of site location - https://www.reddit.com/r/WIX/comments/tax9t1;hard code viewport - https://www.reddit.com/r/webdev/comments/vp28k8/comment/ieginbe/;MAYBE THIS IS TIED TO WEBSITE "BACKGROUND COLOR" ELEMENTS?? scrolling the page = color layers moving
0hXkz9I8-ESlp5VewyqiOGUADNcX | refresh L4v /Joe logos | JOE'S REQs & REQs [REQUESTS+REQUIREMENTS] | Not started | Medium |  | Brian Baker | 04/06/2025 |  |  | false | false |  |  | 0/2 | re-do silhouette logo using joe's outline;".com" logo ending?
19GOFDiCT0iuvY-edJ66eGUAIf0f | stella docusign email notifs | low priority | Completed | Medium | Isabela Almeida | Brian Baker | 03/31/2025 |  |  | false | false | 04/20/2025 | Isabela Almeida | 5/6 | stella@law4veterans.com seems to be a default recipient in the notification flow;CAN STELLA JUST HIT "UNSUBSCRIBE" LINK ???? (mostly no);debbie@, stella@ both trigger email to stella@ when they send envelope to client;unclear if joe@ also triggers;evaluate fix;what does "report email" hyperlink do?
1OV-fUPcCU2DkYHgW17TUWUAEXay | wix certs | low priority | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/2 | https://www.wix.com/learn/certification/accessibility;https://www.wix.com/studio/academy/web-designer-certification-criteria
1zL2Oil0BEiIzKCR70R4fWUAA8_n | instagram, intro triple postsss | URGENT - DO THIS NOW | Completed | Urgent |  | Brian Baker | 03/31/2025 |  |  | false | false | 04/08/2025 | Brian Baker | 4/4 | r1) open with branding? jeep, dogtag?, logo??;r2) (PIN) about joe, about l4v, why we're different;2) contact info (use ig app);3) l4v generic (use meta app) | URGENT;social media
2Hyf4uhHvUyc5J-zwO2zLGUAMpUO | When do I ask for Joe's input? | Questions for emails | Not started | Medium |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 0/1 | asking for input before every step = nothing gets done
2uv90C4nvkaZd98LkbjigmUAGf6x | photo export settings: instagram (+facebook crosspost) | URGENT - DO THIS NOW | Completed | Medium |  | Brian Baker | 04/06/2025 |  |  | false | false | 04/07/2025 | Brian Baker | 0/1 | IG (1080 x 1350): 4:5 portrait... 1080p width
31R82bNYjEunzQHnG_UPqmUAECY7 | Complete account setup | GOOGLE ANALYTICS | Not started | Medium |  | Isabela Almeida | 04/17/2025 |  |  | false | false
3gthW98PZ0uBiUFWH7GLmmUANxJe | email campaigns | MAJOR TASKS | Not started | Important |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/4 | holiday + military holiday;newsletter;dropped/silent Leads;client birthday > simplelaw??? outlook?
4XrBG9yP7UO5x6Nrb4bIbGUAIjGc | FIX META BIZ SUITE??? | URGENT - DO THIS NOW | Completed | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false | 04/15/2025 | Brian Baker | 0/6 | attach ad accounts to biz portfolios + assets (both L4v and bbdigital);Separate ig and FB logins (meta accounts panel);Try allowing all cross logins for Brian accounts to access meta biz suite? Try adding individually;Check Joe biz suite admins.... Add both my accounts (bakerb/fb and bbdigital/ig);RESEARCH: meta work account?? Account assigned by admin;Add 2fa sms # to personal acct? | URGENT;social media
4u44clbXsUGHq728M_B2bGUAEm10 | google partner????? FK troy | No Bucket | Not started | Medium |  | Brian Baker | 05/10/2025 |  |  | false | false |  |  | 0/1 | https://enterprisemarketingportal.google/become-a-partner
5Rp2gPIWYkWE-XCp9lAvSGUAOtCN | Notes for Website | URGENT - DO THIS NOW | Not started | Medium |  | Isabela Almeida | 04/20/2025 |  |  | false | false
6A1ThAsNXka7rLXo5CqEcWUACPVo | CAPTIONS | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/1 | saved here > https://keep.google.com/u/0/#label/%23%23L4V%20captions
6BtDvO3n8Eu96aPJN9lXg2UAEbLS | Upload Media Assets to File Manager on Meta | SOCIAL MEDIA | Not started | Medium |  | Isabela Almeida | 04/08/2025 |  |  | false | false
6hYsOnzS4kyTLTqZmIDduGUAFjxo | L4V CASE HISTORY | L4v "databases" [DB] | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/3 | spreadsheet: client, date of contact/appeal/ruling, injury/claim, geo locale, $award (+fee);Generate using copilot + prevail files?;SEE JOE's SPREADSHEET (in bbdigital email) - (2022-24?) | [databases]
7-QxU3bqVECLn8QZoYDJf2UAPNqR | L4v phone numbers - public facing | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 0/6 | facebook;website;-4044 = Twilio (no access?);[“real” #s == 704-543-2294 and 704-940-0353];7045432294 - IG @joe_vets_lawyer;nc bar records | phone numbers #
7EcXUEvQ1Ui865NnYaX4RGUADWOX | Code to auto adjust size | WIX WEBSITE | Not started | Medium |  | Isabela Almeida | 04/29/2025 |  |  | false | false |  |  | 0/1 | https://www.wix.com/blog/responsive-website-design
8SUDWzFspk-QEejgbCr99mUAJPjo | google search console | low priority | Not started | Medium | Isabela Almeida | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/5 | 1: added L4v domain via search console panel ;TWO properties?? ;https://www.wix.com/seo/learn/resource/wix-site-inspection-tool;reddit says: check html header for old tag data;2: added google tag via wix marketing integrations
8mec1RbGp0K0RhAvNg7BjGUAE5kT | Joe requests | JOE'S REQs & REQs [REQUESTS+REQUIREMENTS] | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/1 | remove dates from google reviews?
8z_ZFG9NV0ikz_aVEcqgKGUAINtU | media export settings for Wix uploads | WIX WEBSITE | Not started | Medium |  | Brian Baker | 05/06/2025 |  |  | false | false |  |  | 0/5 | https://support.wix.com/en/article/site-performance-optimizing-your-media;https://support.wix.com/en/article/wix-media-supported-media-file-types-and-file-sizes;image formatting tool ... https://squoosh.app/;https://support.wix.com/en/article/optimizing-your-images-and-galleries-for-seo-alt-text;https://forum.wixstudio.com/t/is-anyone-already-using-avif-images-on-wix/65121
AHsqmdIjxEOCl4x6DPC332UAMEJz | L4V branding kits | low priority | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/4 | fonts, styles, colors;wix;adobe;canva
ATLiZ6MIx0GO7YQ3W1lox2UAKomN | Should we be using landing pages? Are they already in use? | WIX WEBSITE | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false
BSikznaz90i1R3FN_vYMw2UAMX6z | Phone numbers | TO DO, this week | Not started | Medium |  | Isabela Almeida | 04/06/2025 |  |  | false | false |  |  | 0/3 | research: call rail, nextiva, twilio .. multi-number setup for analytics, campaigns ;brian: reply to Twilio email;Joe's 300-4VET new number? | external help tickets;phone numbers #
BXyD5PwLoEifdJStaNDby2UAHbkX | JOE BRANDING REQUESTS | JOE'S REQs & REQs [REQUESTS+REQUIREMENTS] | Not started | Important |  | Brian Baker | 04/18/2025 |  |  | false | false |  |  | 0/2 | love original american flag + dogtag logo ;love "go with joe" logo > change graphic to joe's silhouette > headshot + photoshop > indesign? | Joe
DCeyG58HXkqO22l_8nYxNGUAEPjs | SEO | low priority | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/3 | https://www.reddit.com/r/SEO/comments/hrcbv9/wix_seo_issues/;https://www.reddit.com/r/WixHelp/comments/18oazro/meta_descripton_business_what_am_i_missing/;https://www.wix.com/seo/learn/resource/what-is-google-search-console#viewer-5ybih31321
DUaldD9-ZESCGQzp3sdHsGUAN_lt | Brian owned | google conversion tags | Not started | Medium |  | Brian Baker | 04/16/2025 |  |  | false | false |  |  | 0/4 | L4V tag mgr container - GTM-54HN8L4T ;G-0HGTJKFYN0... wix google tag integration;Law4Veterans Google Tag Mgr - 629 129 990 6;L4V GAnanlytics Account - 346 616 544
DuxguSs9L0Wx7o8o2jFjq2UAJnsJ | PENDING RESPONSE | Questions for emails | Not started | Medium |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 0/1 | (Joe) no fee "until we win" vs "unless we win"
DvJZuivRSEaZ4xAQOKI1nWUAHJ7p | "vibe" streaming service commercials | TO DO, this week | Not started | Medium |  | Brian Baker | 04/14/2025 |  |  | false | false |  |  | 0/2 | attach ad pixel(s) to website;fix google tag mgr
EkXxnFsu9EyA04XRIWXpHWUAH2D3 | Joe Headshots | URGENT - DO THIS NOW | Completed | Medium |  | Brian Baker | 04/06/2025 |  |  | false | false | 04/07/2025 | Brian Baker | 0/2 | final edits (color temp) ;best export settings?
EybbSMbHLU6jgsPCd_uiT2UAOs65 | VA language, official usage | Questions for emails | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/1 | VA claims == va disability claims?
FPe1z6RzZ0umxMfhtcOvdmUAERFB | Wix Form spam | URGENT - DO THIS NOW | Not started | Urgent |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 1/3 | does moving OFF front page help? ... ask support ;captcha is active in settings. does it need to be added as form element?;See help ticket reply: bbdigital inbox | external help tickets
FgFMC6To90uhf1uEx2DBTWUANH8J | Update dns domain tags with MS, Wix, DS | For Longevity sake | Not started | Medium |  | Isabela Almeida | 04/22/2025 |  |  | false | false
GdsJfBufGEaNHUfjStYzT2UAHUom | ??????? wix | l4v website, low priority | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/2 | how the fuck do containers work;customize org links / assets / socials icons??
Gx0weEfq1EWP8yy3slC_pGUAAQKn | Wix form (soon intaker chat) - Lead notif email | URGENT - DO THIS NOW | Not started | Urgent |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 0/3 | use "OLD FORM" for inbox reply-to-Lead fxn (ARTICLE ABOVE);Wix email notif: "From: Joe Bochicchio ¦ Law4Veterans.com" ... remove Joe B;change pfp to Joe or L4V logo? | WIX SHIT;intaker
HXPOnA5tQEGvkVi2nTAUDmUAIRPD | clean up L4V/DLH msft project files | low priority | Not started | Low | Isabela Almeida | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 0/2 | delete Planner stubs, archive old;start in Sharepoint?
IG-yIaOMtECxpiBGDMg9FGUANKrN | Speed Optimization Analysis | WIX WEBSITE | Not started | Medium |  | Isabela Almeida | 04/10/2025 |  |  | false | false
IfZR-P0YBkO072njsl3NOmUAJ4py | google analytics | low priority | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/2 | UTM ;configure site tags: analytics>L4V account>property settings>data streams
IwRVuUF3CEGnjSikFr4CxmUAGSeI | Misc usage, ethics | Questions for emails | Not started | Medium |  | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 0/2 | lawyer vs attorney vs law firm;https://www.ncbar.org/2019/07/23/ethical-considerations-for-nc-law-firm-websites/
IxgnJV2a-EaeYwllwqOhw2UAPw8q | RESEARCH | l4v website, low priority | Not started | Medium |  | Brian Baker | 04/10/2025 |  |  | false | false |  |  | 0/2 | https://dev.wix.com/docs/develop-websites/articles/workspace-tools/developer-tools/triggered-emails/;triggered emails vs wix automations. same thing?
J5UyYI5eHESZPlFzH8Z5S2UAFiP7 | May Social Media Post ideas | No Bucket | Not started | Medium | Isabela Almeida | Isabela Almeida | 04/28/2025 |  |  | false | false |  |  | 0/2 | May 11 is Military Spouse Appreciation Day;Military Appreciation Month
JKbbbgkuhEOQpAi_ZeOhimUACHFI | [DB] BRAND COLORS ... hexcolors, etc. | L4v "databases" [DB] | Not started | Medium |  | Brian Baker | 04/18/2025 |  |  | false | false |  |  | 0/3 | Intaker OG (bold blue): 498fe1;Canva 1 (LT blue): 7dc1ff;Canva 2 (DK blue): 6995b5 | social media;[databases];L4V Branding
K-HY1zlfH02t0P2QRCCTQ2UADRWF | LATER /intaker side projects | INTAKER INTALL 2K25 HAPPY EASTER | Not started | Low |  | Brian Baker | 04/18/2025 |  |  | false | false |  |  |  |  | intaker
K2tneR2pnUOaRX4pwdyI92UAETk- | Legal Taxonomy resource for VA terms | L4v "databases" [DB] | Not started | Medium |  | Isabela Almeida | 04/07/2025 |  |  | false | false
KL3gUqJVikiC16H8pzNoWmUAO3o1 | to do | google conversion tags | Not started | Medium |  | Brian Baker | 04/16/2025 |  |  | false | false |  |  | 0/3 | REQUIRES: ads campaign admin access;edit individual campaign's settings for analytics referrals (tag settings) ;determine which campaigns troy wants linked to what website actions
L1FALW8zfE24rO42WPvkUmUAIeOt | database for L4V usage rules, technicals, ethics | L4v "databases" [DB] | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/4 | "established" dates;Biz entities: jmb pllc;accolades, bona fides;DBA? | [databases]
LZ_ptQyJQ02x01vMrwXQ12UAM0uN | custom "socials bar" | l4v website, low priority | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/4 | google reviews/business;avvo?;linked in;put them in the footer... == google reviews on every page
LaOOFBrrbUOEL8vYoSlHFWUABDRR | Intaker = poor mobile experience? | INTAKER INTALL 2K25 HAPPY EASTER | Completed | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false | 04/22/2025 | Brian Baker |  |  | WIX SHIT;intaker
Lrk7ivSt-Emlmv9LO98OnWUANjn1 | Create a link with Google Ads | GOOGLE ANALYTICS | Not started | Medium |  | Isabela Almeida | 04/17/2025 |  |  | false | false
M-6fRrDO9U2MJLl1TyHQJmUANK9t | TROY DO THIS SHIT - google ads | google conversion tags | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/5 | Conversion Action ... Set conversion value ??;TRACKING TEMPLATE to BLANK???;GIVE ADMIN?: cannot link to g.analytics account;enable parallel tracking;account setting > lead form ads terms NOT accepted
MSWE-2uA20mgSsCrw7KQP2UABfJy | ad blocker incompatible? | WIX WEBSITE | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/2 | website flashes and reloads on my phone (adguard);test intaker bot v2
N1AWV9g-dEi73EjGAL2jqmUANQBc | [DB] BRANDING PACKET /LIBRARY | MAJOR TASKS | Not started | Medium |  | Brian Baker | 04/18/2025 |  |  | false | false |  |  | 0/3 | logos;colors: ;wordmark
Nc_gBGSzJE2HkC3OiJ74T2UAPO_u | Jessica's website | L4V x Wayback Archive | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false
OKyCstt-VkWES7FHs5ZRf2UAF6dY | Facebook | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/3 | finish the easy-graphic for stella (finished? check email) ;start ads campaign;QR +UTM codes (decide on google analytics tags??)
OeeDdny2OE-SH38c0HstfGUABYbJ | https://www.youtube.com/@Law4Veterans | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false
P5EA7vFD9UO3spVBROIAmWUAAJf1 | database ideas | L4v "databases" [DB] | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/10 | points of contact (phones, emails);licenses, memberships, bonafides;hashtags;(disentangle DLH~L4V);review website profiles - google biz, avvo, trust pilot, etc;competitors/inspo;ad copy usage rules;accolades;digital asset map (photos, logos, media packet,);social media profiles | [databases]
PENQVlMIUE-KLNeNS7OA5mUAPAqh | [DB] FACEBOOK / META RESOURCES | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 0/4 | fb page admin: https://www.facebook.com/professional_dashboard/overview/;https://www.facebook.com/business/help/support;https://play.google.com/store/apps/developer?id=Meta%20Platforms%2C%20Inc.&hl=en_US;https://www.facebook.com/help | social media;[databases]
PJqIKZcEtkiMnS52H_IOxWUAONQh | NEED L4V MEDIA FOR... | No Bucket | Not started | Medium |  | Brian Baker | 05/10/2025 |  |  | false | false |  |  | 0/1 | Big l4v logo file (1:1 square, 10mb) for Google Biz Profile pic
PoTp4BnkkUq3aWTHRyoInGUACw_d | competitors / inspo | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/03/2025 |  |  | false | false |  |  | 0/3 | 1300 folowers - https://www.instagram.com/ptsdlawyers/;4500 folowers - https://www.instagram.com/veteranslegalinstitute/;1200 followers - https://www.instagram.com/woodsandwoods/
Q6Z1TfUCUkuNhJ2gkXhSGWUAPKDx | audit /update L4V phone numbers | MAJOR TASKS | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 3/9 | trace numbers to campaigns (/platforms?);wait for Troy's report (email) ;Troy: defaulting 704-940-0353 (joe says "that's one of my actual land line numbers");(product) research > phone # generator +analytics ;see @isa notes for #s;bbb.org: (704) 940-0353;Troy : all L4v-800 numbers untrackable;DATABASE: L4v #s, attached channel,;attach (unique?) #s to every profile > IG, FB, website, ads | phone numbers #
QVlK0MR18E24_daqggd8bWUAOOw_ | OPSEC | upcoming | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/6 | outlook inbox search: "unsubscribe";open support ticket: when was rule "antispam" created? > matthewdonchester2023@gmail.com;segregate email addresses.. biz and personal;remember Stella's bitwarden password....;set up bitwarden for Joe and Stella....;Set brian as their bitwarden admin
Qc4RmVVQi0Sl7XlRgaHrcWUAAkiV | Search Console link to backlinks | l4v website, low priority | Not started | Medium |  | Isabela Almeida | 04/17/2025 |  |  | false | false
QjPXVk2tMESZEbxRFFUCtGUADp2t | L4V v3.0 chatbot - intaker high level TO DO | INTAKER INTALL 2K25 HAPPY EASTER | Not started | Urgent | Isabela Almeida | Brian Baker | 04/18/2025 |  |  | false | false |  |  | 4/12 | add instructions re: how Leads submit Letters... email, scan,....?? ;"Text us widget" ... joe says "sure, just not my cell. do later;BOT (v3.0), WORKING VERSION >>> https://www.intaker.com/law4veterans/L4Vv3.0;"contacts widgets" ... unknown. likely cannot claim current L4V 1-866-num from Twilio ;remove ALL emojis (default responses) ;edit popup text in "mini widget" and "pop up" > worded so we aren't initiating contact;future research: sequences, workflows, integrations, analytics, Leads (2022-2025) .... ;---;INSTALL ON WEBSITE, replace wix chat;complete "landing page" ... low priority. pic? colors?... link to Ads/tag mgr eventually;future tasks: update Organization profile;apply remaining joe edits??? shared reply-to inbox? etc. | URGENT;intaker
RamTcYxSRkiydhnwP3QDl2UAACDE | wix: prep for OUTSOURCE | No Bucket | Not started | Medium |  | Brian Baker | 04/28/2025 |  |  | false | false |  |  | 0/2 | update theme... fonts + sizes, colors;create wix asset Boards (org assets)
SXBcvaxndkqpXovtQ6vA3WUAM3_P | ian, social media | TO DO, this week | Not started | Urgent |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 5/8 | send assets;add to IG, FB admin;work on twitter, linkedin, ;https://metricool.com/crossposting-instagram-facebook/#Crossposting_from_Instagram_to_Facebook_from_;(Ian) does his account work? ;https://help.instagram.com/192857082456744;ask his content/design ;ian posts to IG > auto-post to FB page | TODO this wk;URGENT;social media
T209kAnbBU6pufWklTO43WUALLfH | law4veterans.com/#burn | L4V x Wayback Archive | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/1 | [INSERT ARCHIVE LINK]
T2hGSs0Yxk2SLG37mYuZGWUAA3Vx | Fix mobile layout | WIX WEBSITE | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/2 | https://support.wix.com/en/article/wix-editor-troubleshooting-layout-issues-on-your-mobile-site;https://support.wix.com/en/article/site-performance-best-practices
TIHmINgC1EKz0q9VanHAP2UAPgLM | incomplete website SEO? | WIX WEBSITE | Completed | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false | 04/28/2025 | Brian Baker
TtFshuDr8UC0d0Ha2icMlWUAAsvy | l4v logos | URGENT - DO THIS NOW | Completed | Medium |  | Brian Baker | 04/06/2025 |  |  | false | false | 04/07/2025 | Brian Baker
UWv1KP8OOEORqIRUA2ygV2UAF0iL | Troy's website | L4V x Wayback Archive | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false
VUSUYXQLU02U2Cv7o8aw4WUAB7ZU | google ads settings | GOOGLE ANALYTICS | Not started | Medium |  | Brian Baker | 04/16/2025 |  |  | false | false |  |  | 0/2 | goals > conversions > summary > settings > google analytics property ;conversion id, destination id - AW-11030537154
VlqIxyxq0UCA2arvabcR3WUAH_K_ | web vs desktop apps | low priority | Not started | Low | Isabela Almeida | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/2 | canva;misc meta business shits
VoCVi0zO0UG6HxZ4aIwpTGUAIh1n | google tag mgr | google conversion tags | Not started | Medium |  | Brian Baker | 04/16/2025 |  |  | false | false
WTpIqKDJ8EGXhdzhzUYCSmUAPGYl | Competitor | Isa | Not started | Medium |  | Isabela Almeida | 04/20/2025 |  |  | false | false |  |  | 0/1 | https://ptsdlawyers.com/board-of-veterans-appeals/
WVQdc8gWoU-JS2-sVHv36mUAIH31 | L4V DIGITAL ASSET MAP | WIX WEBSITE | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/6 | g photos - headshots; proofs, https://photos.app.goo.gl/yCDJkxfoR6G8TLDu8;gdrive - assets for Ian (headshots, logos) ;gdrive - canva exports (socials posts) ;canva - socials posts;g photos - jeep, NC, https://photos.app.goo.gl/APg5pXWnmUGCkcFr9;Headshots draft edit v1 vhttps://photos.app.goo.gl/yCDJkxfoR6G8TLDu8 | [databases];WIX SHIT;L4V Branding
XBBc3Nd_GkSkzC2Zp27P6WUAMSfX | accounts and pages to tag | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/2 | wounded warrior project? etc;ask joe
Xd7zALMqpU-_-X9qoK0wN2UAGxSd | wix font themes | WIX WEBSITE | Not started | Medium |  | Brian Baker | 04/28/2025 |  |  | false | false |  |  | 0/1 | https://support.wix.com/en/article/wix-editor-working-with-text-themes
ZCjQxB46EUaeY8tqIBLgamUAHkxV | Schema guideline to improve SEO | Isa | Not started | Medium |  | Isabela Almeida | 04/07/2025 |  |  | false | false |  |  | 0/3 | Brian says: actually writing seo tags, etc., must happen before improvement planning.;Excellent resource is Yoast (check for wix plugin?);Probably excellent resource is Wix seo checklist/wizard
_swP6JhRDkWIz8fA51RVC2UAJVVC | [DB] L4V HASHTAGS (fb, ig) | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/2 | #JosephMBochicchioPLLC #GoWithJoe #Law4Veterans;#serviceconnected | social media;[databases]
aeTQ1DgcoUyfsSlAo4Y87WUALx0J | Meta | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/9 | reply to open FB tickets;claim fb@law4veterans;verify phone # tied to Joe IG profile > accountscenter.instagram.com/profiles/;UNLOCK INSTAGRAM?!?!?;open help via IG;Get meta verified ;Verify Joe personal identity (mail 2fa from Debbie) ;attach all accts to accountscenter.instagram.com ;open addtl FB help
am6DKIHyr0GHR6usOwGrzGUAOJ3F | FAQ page | l4v website, low priority | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/2 | can dynamic collection display like i want;dynamic collection FAQ in place of blog? SEO implications?
awCgnaU_s063f_-GKjwogWUALz3l | Landing page?? | L4V x Wayback Archive | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false
bZCCDszhwEyBdSfsrEef5mUAI58J | Finish website | WIX WEBSITE | Not started | Urgent |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 7/15 | INTEGRATIONS: G tag vs tag mgr? ;SEO: meta tags for literally every element, asset filenames (native vs wix?) ;fix mobile layout menus;ASSETS: edit pics, logos;MENUS: mobile and desktop;fix mobile layout zoom issue;https://www.reddit.com/r/WIX/comments/17s9x2y/best_practices_uploading_images_and_saving_records/;apply joe intaker edits;shrink mobile layout elements;fix mobile layout font size;install intaker;INTAKER: request joe audit;MOBILE SITE: fix layout;CONTENT: faqs... ;Update website socials info/icons | WIX SHIT
cBNjcTEo8kiYfBb1BaAAo2UADYeR | psych doc search | TO DO, this week | Not started | Urgent | Isabela Almeida | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 1/5 | MD or PhD ... see joe email for reqs;compile list, send to joe ;(wix form) Alex Rosin, MD ALEXROSIN4@GMAIL.COM https://www.linkedin.com/in/alex-rosin-072ba1321;https://www.reddit.com/r/psychotherapists/comments/1iyu0as/where_to_find_clients/;search web, IG, FB, psych today, linkedin, ... VA website?
ciOA1VfJCkajGP1gVKsIWmUAAmL1 | terrible mobile UX | WIX WEBSITE | Completed | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false | 04/22/2025 | Brian Baker | 0/1 | website zooms in for certain users (android + chrome?)
ddKq4zknZEWI_WV9tB2KbWUAHEJk | Simple Law renewal??? | low priority | In progress | Low | Isabela Almeida | Brian Baker | 04/01/2025 |  | 08/01/2025 | false | false |  |  | 1/3 | when?;August;Ditch simple law? Lol
e1kWti6bW0qV2e51OAerk2UAE9r3 | social media | TO DO, this week | Not started | Important |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 0/2 | change PFPs (ig, fb) ;sanitize instagram (followed accounts) | URGENT
fFjEOpYamUG-PpYbHnw9RWUACr7l | Brian Meta account disaster | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 3/8 | my current fb page login = bbdigital email + bakerb user account. disentangle this;https://www.reddit.com/r/FacebookBusiness/comments/1hagop5/unable_to_accept_business_invite/;meta account: disallow cross over logins;fb page admin accounts are tied to email address...;personal FB account cannot use Meta Business Suite ;fb page admin: change bbdigital to bakerb;facebook.com/id/hub > official docs > action required > 'no Q's available' loop;INFO: i have never used/installed FB mobile > incomplete 'identity' feature? > limiting my acct?
fNG4boYtwUWFrGGFllX8YWUAP1Zm | dba/trade name | low priority | Not started | Medium |  | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 2/6 | NC Bar does not care;https://www.ncbar.gov/for-lawyers/ethics/adopted-opinions/2005-formal-ethics-opinion-8/;must register DBA in at least 1 county ;trademark search https://tmsearch.uspto.gov/search/search-information;nc dba form: https://edpnc.com/wp-content/uploads/2024/03/A-Assumed-Business-Name-Certificate-1.pdf;meck county dba: https://meckrod.manatron.com/localization/asninfo.htm
fW4CMJmESECR0LCItstGt2UAI2JI | get GAds under GA4, all under new marketing platform | For Longevity sake | Not started | Medium |  | Isabela Almeida | 04/22/2025 |  |  | false | false
fxrYrIxjUUeA86R0CpbLuGUAIPO_ | Nexus Letter Providers | INTAKER INTALL 2K25 HAPPY EASTER | Not started | Important |  | Isabela Almeida | 04/18/2025 |  |  | false | false |  |  | 0/1 | https://americanmedicalexperts.com/
gLDfLqh-jEyOkgHW9oe892UAFBbs | 🐊 NOTES: intaker readme | INTAKER INTALL 2K25 HAPPY EASTER | Completed | Medium |  | Brian Baker | 04/18/2025 |  |  | false | false | 04/22/2025 | Brian Baker | 0/4 | settings menus have no logic == look thru every setting to change any one thing, lol . . . ;must request "script" changes via support (email);open every drop-down for "advanced settings" == most of the bot features ;working version is "L4V v3.0" | intaker
gfHUlu9_jESMB_wAKDXR2WUAE-Ix | wix themes | No Bucket | Not started | Medium |  | Brian Baker | 04/28/2025 |  |  | false | false |  |  | 0/4 | fonts + sizes according to SEO Hierarchy (H1-P3) ... already done? ;colors;have NOT deployed or tested Theme on live site;Theme SHOULD BE live on https://www.law4veterans.com/va-claims-consultation
h7mkAvax9kCwtxawxWR1BmUABgXR | Joe's INTAKER reqs | INTAKER INTALL 2K25 HAPPY EASTER | Not started | Urgent |  | Brian Baker | 04/18/2025 |  |  | false | false |  |  | 6/15 | [🐊 wanted Lead as reply-to, so Joe decides email contact... use pass-thru inbox, solve 2x probs];LEAD'S EMAIL > how to get/send decision letter;Feb17: consultations@, bcc debbie, stella, joe;[🐊 Intaker Lead info fields is set at the chatbot level, for all chat flows;"don’t care if we use Wix or Intaker ultimately… I just want it all to work";FAQ on the chatbot;edit any "free consultation with *joe*" ,, stella/debbie also do consults;"WIX dashboard is more difficult to use, and we were having trouble getting fill in forms";"use Intaker for leads, and WIX for mobile website leads?";"I agree that if [chatbot mssg is] coming to me, they are only communicating with a lawyer";put debbie@ for RD recipient;LEAD's EMAIL >> “please send us a copy of the RD”…. where would they send it to? ;CHANGE >> "can i help you?" popup = lawyers initiating contact = unethical ;set LEAD EMAIL reply-to = joe@l4v ... Lead can send RD via replying to email ;personalize "chatbot" icons with Joe's pic, name >> edit chat copy to first person? | Joe;intaker
hb_qmdfN-kOfZPLrrAf48mUACSxE | DNS Domain auth keys are on Wix | For Longevity sake | Not started | Medium |  | Isabela Almeida | 04/22/2025 |  |  | false | false
i6PUfT9kF06rEO4gpzvfEGUABIbv | [DB] LIST OF PHONE NUMBERS | MAJOR TASKS | Not started | Medium |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 0/4 | 704-318-4777 - https://www.instagram.com/p/ChKYdh0Or8D/;(704-940-0353 - Troy's default);(704-543-2294) ;intaker > settings > "intaker phone number" (704) 389-9901 ... fwds to (704) 940-0353 | [databases];phone numbers #
iasqDjZAAkykojZHRG0YdmUAJ06v | Biz category | Questions for emails | Not started | Medium |  | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 0/5 | Law Firm ;legal service;Veterans services;legal ;Lawyer
jHEhk7Nv5Ua3NYQZydWM62UAHgGD | Meta Ads policy - fb/ig | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false
jUzEgV7JdEu5_EcgedDvxGUAC57R | Stella msft teams license | upcoming | Completed | Medium |  | Brian Baker | 04/03/2025 |  | 05/20/2025 | false | false | 04/15/2025 | Brian Baker | 0/2 | Awaiting exam instructions from Stella;What else needed for e-exam?
kb1Vnf64lU-5TPmPwyLJEWUAHhUB | Wix Boards | No Bucket | Not started | Medium |  | Brian Baker | 04/28/2025 |  |  | false | false |  |  | 0/7 | ) logos and branding;)) check "asset map" task within this planner for others;) headshots ;can they all go in a single board? then subdivide accordingly ;what is ideal file settings: size, resolution, etc.;write SEO filenames before upload to wix??? or upload naked files, then update in wix?;) large assets, heros, backgrounds (jeep... etc.)
kpwRlz_MtkGRLmJwTNI38GUADf1A | clean up L4V canva folders, permissions | low priority | Not started | Low | Isabela Almeida | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/3 | price check Canva;separate all from guga's account?;any good alts? don't think so
kzEbMTrXPECP-sXQ_k2DaWUAEVCp | test | google conversion tags | Completed | Medium |  | Isabela Almeida | 04/18/2025 |  |  | false | false | 04/22/2025 | Brian Baker
lMwJscYqvUyW96sMP93tD2UAImS1 | generate QR + UTM | upcoming | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/2 | https://www.wix.com/tools/qr-code-generator;figure out UTM tags > google analytics
mJYme3FA20y86SjHmcPa22UAP1Cz | Can Joe access....? | Questions for emails | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/5 | bochicchiolaw@gmail.com > intaker pending users;[pen test] joe@law4veterans and @DLH >> as username for gmail.com ;bochicchiolaw >> 2fa phone ends in -27.... >> j**@law4veterans.com;bochicchiolaw@gmail.com > google ads admin;law4veterans@gmail.com
myhxuZLOd0ClUqjhjwIDhmUAJShj | draft Firm-wide "how to not get hacked" email | upcoming | Not started | Medium |  | Brian Baker | 04/15/2025 |  |  | false | false |  |  | 0/3 | password to passphrase ;"unsubscribe";how to examine outlook email header?/detailed sender info (SENDER DOMAIN)
nJd5M8EWGUO8cedVAslSF2UAGesH | youtube | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/3 | solution? https://www.youtube.com/watch?v=rMQRqKi4FeQ;(https://www.youtube.com/@Law4Veterans);recover account? ... law4veterans@gmail.com
nSIdSz6ny0yAlbs7OI2RVGUAFC7g | EDIT PICS FOR WEBSITE | upcoming | Not started | Medium |  | Brian Baker | 04/08/2025 |  |  | false | false |  |  | 0/2 | SHOOTING PICS w/Sam;g photos - jeep, NC, https://photos.app.goo.gl/APg5pXWnmUGCkcFr9 | WIX SHIT
nhOjU9m48UWu_b0jvd5f82UAO9GI | brianbakerdigital did NOT receive Form completion notification | MAJOR TASKS | Completed | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false | 03/31/2025 | Brian Baker
o7LRrmCyuE27Eu6Qq6wLgmUAG_Ey | L4V CORE BRANDING | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false |  |  |  |  | social media;[databases]
oVujoRibPE2986kpAm2MeGUAOkfq | Joe Qs: social media usage | Questions for emails | Not started | Medium |  | Brian Baker | 04/07/2025 |  |  | false | false |  |  | 0/3 | hashtags approval ;core identity claims;who can we tag in posts
ojw4LvUaw0Os-PdqGkVBwGUAKTMi | Joe bona fides, acolades | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/2 | https://portal.ncbar.gov/verification/search.aspx?ID=28244;https://www.va.gov/ogc/apps/accreditation/accredpeopledetail.asp?ID={40E3B201-2C42-4B1A-A19F-6FE3479
ojwVJLBIrkaqQU8ubT_6BWUAJUw5 | reasons "why we're different" | TO DO, this week | Not started | Important | Isabela Almeida | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/13 | home grown NC;single lawyer;no AI (limit this claim);case/client selective;VA accredited atty;X hundred vets served;bank, BK attorney;one-on-one, human interaction;zero corporate;20 years of experience;20% fee;no jurisdiction limit;family practice | social media;Joe
p70VUSr4EU6V3nRG__cV-GUAJ_9f | Brian notes re: fiverr wix site | No Bucket | Not started | Medium |  | Brian Baker | 04/28/2025 |  |  | false | false |  |  | 0/2 | (review in progress....) ;great menu /banner. especially phone number
pHwPLIldrkS-dkNWhTN2umUAMJQO | scrape copy from old websites | L4V x Wayback Archive | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/3 | wayback > site map;new copy = old copy + SEO keywords ;scrape w/GPT
pRTCY5JpiUybjtwbSPXOz2UAH48Y | intaker install > wix site | INTAKER INTALL 2K25 HAPPY EASTER | Completed | Medium |  | Brian Baker | 04/18/2025 |  |  | false | false | 04/22/2025 | Brian Baker | 0/5 | 2) or use domain rules (/bots/publish) ??? ... not sure if code injection still required;1) inject header code into Wix ... https://dashboard.intaker.com/bots/publish ;remove wix chat, GOOD RIDDANCE MFFFFFFFF;audit / fix intaker+wix mobile website;use Intaker HTML button code?? ... sucked ass when I tried last | WIX SHIT;intaker
pVp96bF20UCWjtwnApDmOmUAF5He | google ads TO DO | GOOGLE ANALYTICS | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 1/3 | law4veterans.com/#burn;check Troy's ads for URLs;tags support says: change conversion goals away from default & point at website instead of e.g. UA
pkwAT5n02UG-_qAccO50pGUAHDMF | L4v accounts /profiles | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/1 | https://x.com/Law4veterans
ptVFa26nk0qrNqq9RthZdmUAHxq7 | edit domain config for tag | GOOGLE ANALYTICS | Not started | Medium |  | Isabela Almeida | 04/17/2025 |  |  | false | false
qDMWSnEsukCj1kCGE74AyWUAMH0y | Email campaign calendar | upcoming | Not started | Urgent | Isabela Almeida | Brian Baker | 04/06/2025 |  |  | false | false |  |  | 0/3 | mil holidays ;holidays;bdays | URGENT;campaigns
rGA0gOvMo0GzmWD2QXG7LWUAIC9g | google tag mgr | URGENT - DO THIS NOW | Not started | Urgent |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/5 | (unless that's a google search console bug?? idr. double check) ;install Vibe pixel (see their support article) ;google tag manager show TWO l4v websites... maybe due to "ghost" header tag html? ;fix google tag manager;https://support.google.com/tagmanager/answer/12329709
rJeYV5NXtkC7n8rdVy9BD2UAGQ0f | Finish installing Google Tags to Tag Manager and Analytics | URGENT - DO THIS NOW | Not started | Medium |  | Isabela Almeida | 04/16/2025 |  |  | false | false
rS9ZGngNoUaB-Vfj0QF2d2UAGWn2 | website sprint | URGENT - DO THIS NOW | Not started | Urgent | Isabela Almeida | Brian Baker | 04/17/2025 |  |  | false | false |  |  | 0/15 | remove wix chat ;install intaker;set joe as reply-to? ;write submission page instructions > /va-claim-consultation;final intaker script edits, profile pic, etc.;------;standalone chat == landing page?? /lander;move contact form off first page and have buttons direct to /contact-us (was /contact-law4veterans?);------;pageload == form submission;-------;joe can reply to Lead by replying to the email (GOOD SHIT) == same as intaker;use as trigger to fire conversion action in troy's G.ADS CAMPAIGN ;change to OLD FORM and activate "email only" notifs ;optimize mobile
t4OMLTopWUyCxQ-c2ImS_mUAM91c | L4V Email blue check (in Gmail) | low priority | Not started | Medium |  | Brian Baker | 04/03/2025 |  |  | false | false |  |  | 0/1 | BIMI? https://support.google.com/a/answer/10911028?dark=1&sjid=17664652614073739543-NA
tKiMeaYXCk6lSn9mG6HtNWUABr74 | fix contact form (joe cannot submit) | MAJOR TASKS | Completed | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false | 03/31/2025 | Brian Baker
u660l7oV7kiOQvBlFIb6KGUANU-U | IG changes | SOCIAL MEDIA | Not started | Medium |  | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 1/4 | pfp;l4v business details;removed Jessica's logged-in device (macOS, nov 2022);sanitize follows/ers
uXxSjeyc_0C5nVrlaB7wR2UAGEYZ | RESEARCH: website Badges?? shit to join??? | l4v website, low priority | Not started | Medium | Isabela Almeida | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/5 | https://www.nclawspecialists.gov/for-lawyers/for-certified-specialists/media-kit/;https://www.nclamp.gov/;https://www.americanbar.org/groups/specialization/organizations-with-aba-accredited-lawyer-certifica;https://www.nclamp.gov/for-military-personnel-family/finding-a-lawyer/;https://www.ncbar.gov/media/730802/legal-resource-finder.jpg
uh-RcKoaREOEOgzeicVZimUACQjJ | Legal disclaimers, policy | WIX WEBSITE | Not started | Medium |  | Brian Baker | 04/04/2025 |  |  | false | false |  |  | 0/4 | "not legal advice" per page, per FAQ article;any others reqd?;privacy policy?;geo service area (good for SEO and stupids)
vOmyb5LGqk24j7M2XadmdWUAEIM7 | Docusign renewal - APRIL 22 | TO DO, this week | In progress | Urgent | Isabela Almeida | Brian Baker | 03/31/2025 |  | 04/22/2025 | false | true |  |  | 2/4 | review joe's fwd ;review new DS tiers;schedule Docusign demo (Maestro) ;date: TBD
v_-nd7QTgk2x8uwxpqIazGUAJqT- | google analytics, old setup | google conversion tags | Not started | Medium |  | Brian Baker | 04/16/2025 |  |  | false | false |  |  | 0/4 | conversion ID 11030537154... found in G.ads > goals > campaign action settings > tag options ;Troy owns google ads account;OLDER > "Law4Veterans.com. Joseph M. Bochicchio, PLLC (UA-249921957-17)";??? owns google analytics property "Law4Veterans.com. Joseph M. Bochicchio, PLLC - GA4 (401830982)"
vxpml1PKIEGoPJ5oFkEfk2UABhzH | 🧞: Conduct Cybersecurity Audit | upcoming | Not started | Medium |  | Isabela Almeida | 04/08/2025 |  |  | false | false |  |  | 0/3 | Create a data breach plan, and disaster recovery plan/ business continuity;Ask Scott if Cybersecurity for the firm is within his scope ;Teach staff about email encryption
w0GFk3Zyk0ycYf-gDEu_dGUAGvlK | research stubs | l4v website, low priority | Not started | Medium |  | Brian Baker | 05/06/2025 |  |  | false | false
w3bRe26-dUS81XqLQHzHRmUAG721 | where update joe prof pics? | SOCIAL MEDIA | Not started | Low | Isabela Almeida | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 1/8 | finish headshots, export finals;outlook;facebook business page;fb personal acct;ig business acct;yelp;gmail?;google business page / acct
wIvzeeuQtESwXKhkHfmynmUAAoLq | choose: Wix chat vs Intaker | MAJOR TASKS | Completed | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false | 03/31/2025 | Brian Baker |  |  | intaker
wz2_ZuguKE-VQEVNex4WYWUAEKQ1 | scrape archived L4V sites (wayback machine) | l4v website, low priority | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/5 | audit additional pages, URLs;determine useful website versions and their dates;save URL of each;(ChatGPT) old copy + SEO keyword analysis = new copy ;scrape copy and save to... OneNote?
y93dGUrHokWHduEdTPNBaWUAOIdV | Qs for Joe | Questions for emails | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 2/8 | is SMS a valid Lead contact method? ... include "text me" option on forms?;"most recent va decision letter" ... do i need to clarify which letter? or clarify multiple is ok?;VA Decision Letter .... vs ratings decision? need an official glossary (SEO shit) ;joe does free consult 100% of the time? ;is the Wix Contact Form simple enough for LCD Leads? ;Is Nextiva your only biz number provider?;Sender identity in chatbots... initial messages from L4V or from Joe ?;please evaluate/correct consent box
yUMqfKt5REuPMtPK8hEwa2UAH-Er | create shared GPT account for [org] | upcoming | Not started | Medium |  | Brian Baker | 04/16/2025 |  |  | false | false |  |  | 0/1 | alh ?
yfWh6Xw4fUGgmjB0Vb6QuWUAKqb0 | create L4V roles/users/aliases (m365) | L4v "databases" [DB] | Not started | Medium |  | Brian Baker | 04/01/2025 |  |  | false | false |  |  | 0/4 | shared docusign inbox?;create report / spreadsheet (copilot?);marketing@;admin@
yliqJL54T0KSr2ufP9Q3-WUAFq5L | intaker Qs for Joe | INTAKER INTALL 2K25 HAPPY EASTER | Not started | Medium |  | Brian Baker | 03/31/2025 |  |  | false | false |  |  | 0/6 | assign Leads within Intaker? (> research Docusign integration) ;spam prevention? = 2fa sms to submit again;or Joe simply fwd Intaker email regardless?;use intaker phonecall button or intaker phone service? ;live-call connect? intaker instantly dials Firm upon Lead phone # submission;do we need Firm users saved in Intaker? Stella, Debbie, etc. | intaker

## Plan name
Plan name | 🚩🚩[L4V ACTIVE PLANNER]
Plan ID | 6xDVICJT3EKo6jiDxVDKe2UABg3_
Date of export | 07/27/2025